# Project Progress Tracking Form

IS52018C Software Projects 2018

|  |  |
| --- | --- |
| **Project Name** | Augmented Reality Navigator |
| **Project Number** | 14 |
| **Document Start Date** | 08/10/2018 |
| **Business Plan Objective** | To develop a navigation assistant application for composited structures and spaces, specifically looking at museums |
| **Sponsor/Supervisor** | Basil Elmasri |
| **Project Manager** | Jonathan “JT” Tang |

|  |  |
| --- | --- |
| **Budget/hrs** | |
| Resource Name (Student Name) | Budget/hrs |
| Hamza Sheikh | 220 |
| Jonathan Tang | 220 |
| Hardik Ramesh | 220 |
| Nicholas Orford-Williams | 220 |
| Arif Kharoti | 220 |
| Gabriel Sampaio Da Silva Diogo | 220 |

**Status/Progress**

|  |  |  |  |
| --- | --- | --- | --- |
| **Date** | Task ID | Status | Resources Used: Name & hrs |
| 08/10/2018 | 001 | Conceptualising potential software project ideas | All members / 3h30m |
| 10/10/2018 | 002 | Conduct research based around discussed idea | All members / 1h ea. |
| 15/10/2018 | 003 | Discuss prospective stakeholders | All members / 1h ea. |
| 15/10/2018 | 004 | Create questionnaire to attach in contact with stakeholders, gather requirements | Gabriel, Hardik / 1h ea. |
| 15/10/2018 | 005 | Send emails and get in contact with stakeholders | Arif / 1h |
| 15/10/2018 | 006 | Market Research: current solutions to the existing problem, competitors, studies on museum visitors’ behaviour and the retail experience, regulations and standards, footfall in museums | Nicholas, Hamza, JT / 7h ea. |
| 22/10/2018 | 007 | Model Driven Development: Use Case Diagram | JT / 1h |
| 22/10/2018 | 008 | Model Driven Development: Activity Model | Hardik, Arif, Nicholas / 1h ea. |
| 22/10/2018 | 009 | Model Driven Development: Write-up | Hamza, Gabriel / 1h ea. |

**Milestone Revision Plan**

|  |  |  |  |
| --- | --- | --- | --- |
| Milestone ID | Revision Plan, including budget revision | Existing Milestone Date | Revised Milestone Date |
| 1 | Introduction to Software Projects & Project Planning: Concept Defined | 08/10/2018 | 12/10/2018 |
| 2 | Requirements & Market Study | 15/10/2018 | 19/10/2018 |
| 3 | Model Driven Development: Service Model Presented | 26/10/2018 | 26/10/2018 |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
| **Cumulative Resource Usage/hrs** | | | |
| Resource Name | Hrs Used | Hrs Remaining | Revision Date |
| Working Time | 42 | 1278 | 26/10/2018 |