## Sheet1
[11 empty] | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4
|  |  |  | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M
|  |  | Deadline | 2019-03-23 | 2019-03-24 | 2019-03-25 | 2019-03-26 | 2019-03-27 | 2019-03-28 | 2019-03-29 | 2019-03-30 | 2019-03-31 | 2019-04-01 | 2019-04-02 | 2019-04-03 | 2019-04-04 | 2019-04-05 | 2019-04-06 | 2019-04-07 | 2019-04-08 | 2019-04-09 | 2019-04-10 | 2019-04-11 | 2019-04-12 | 2019-04-13 | 2019-04-14 | 2019-04-15 | 2019-04-16 | 2019-04-17 | 2019-04-18 | 2019-04-19 | 2019-04-20 | 2019-04-21 | 2019-04-22 | 2019-04-23 | 2019-04-24 | 2019-04-25 | 2019-04-26 | 2019-04-27 | 2019-04-28 | 2019-04-29
1 | Abstract | Hamza |  | 2 Th: 2
Rough deadlines
0 | Contents |  |  | 2 Th: 2 | Week 0 | Plan
0 | List of Figures |  |  | 2 Th: 2 | Week 1 | Draft 1 - part a
0 | List of Tables |  |  | 2 Th: 2 | Week 2 | Draft 1 - part b
0 | Nomenclature |  |  | 2 Th: 2 | Week 3 | Fixing up and auditing draft 1
[42 empty] | Week 4 | Finalising and submission
1 | Acknowledgements | JT |  | 2 Th: 2
| 1. Introduction |  |  | 2 S: 2
1 | - Motivation | Hamza |  | 2 S: 2
1 | - Purpose & Scope | Hamza |  | 2 S: 2
1 | - Assumptions | Hamza |  | 2 S: 2
1 | - Coverage | Hamza |  | 2 S: 2
2. Background and Literature Review | bar: 1 S
1 | - Background | Nick | bar: 1 S
1 | - AR Libraries | Gabe | bar: 1 S
1 | - Software architecture (& and other tools we analysed) | Hardik | bar: 1 S
1 | - Arduino & Raspberry PIs | Nick | bar: 1 S
3. Project Management Processes | bar: 1 S
1 |  | JT | bar: 1 S
1 | - SDLC | JT | bar: 1 S
1 | - TDD | JT | bar: 1 S
1 | - Repository management | JT | bar: 1 S
4. Requirements | bar: 1 S
1 | - Gathering (BRS, UML) | Nick | bar: 1 S
1 | - Stakeholders (sponsor, users, museum people developers) | Nick | bar: 1 S
1 | - System | Arif | bar: 1 S
1 | - Functional | Arif | bar: 1 S
1 | - Non-functional | Arif | bar: 1 S
5. Design | bar: 1 S
1 | - Models | Gabe | bar: 1 S
o Use case | bar: 1 S
o Activity | bar: 1 S
o Sequence | bar: 1 S
1 | - UI | Hamza | bar: 1 S
1 | - Technical Architecture | Gabe | bar: 1 S
1 | - Accessibility | Arif | bar: 1 S
1 | - User consultations | Hamza | bar: 1 S
6. Implementation
1 | - Backlog | JT |  | 2 S: 2
1 | - Sprint outline (planning, conducted, burndown) | JT |  | 2 S: 2
1 | - Front-end | Hamza |  | 2 S: 2
1 | - Back-end | Gabe |  | 2 S: 2
1 | - Hardware | Nick |  | 2 S: 2
1 | - Challenges | Gabe |  | 2 S: 2
7. Testing & Quality Assurance
1 | - Types of testing conducted | Hardik |  | 2 S: 2
| o Unit Testing |  |  | 2 S: 2
| o Integration Testing |  |  | 2 S: 2
| o Performance and Stress Testing |  |  | 2 S: 2
| o Regression testing |  |  | 2 S: 2
| o UAT Testing |  |  | 2 S: 2
| o Beta Testing |  |  | 2 S: 2
1 | - Deployment | Hamza |  | 2 S: 2
1 | - Formative evaluation | Arif |  | 2 S: 2
1 | - Functional requirements review | Arif |  | 2 S: 2
1 | - Non-Functional requirements review | Arif |  | 2 S: 2
| 8. Project evaluation |  |  | 2 S: 2
1 | - Summative evaluation |  |  | 2 S: 2
1 | - Future developments | Nick |  | 2 S: 2
Appendices
| User & Stakeholder research | Nick | bar: 1 S
| User stories | Hardik | bar: 1 S
| Documentation plan | Hardik | bar: 1 S
| Testing plan | Hardik | bar: 1 S
| Deployment plan | Hardik | bar: 1 S
| Testing | Hardik | bar: 1 S
| User & Stakeholder feedback | Hardik |  | 2 S: 2
0 | Bibliography